## Bid Form
UPDATED ATTACHMENT B COST SHEET FOR ADDENDUM #8
Brown County Port & Resource Recovery
Port Development Project - 2767A
Contractor Bid Form
Contractor Name:
Bid Schedule A - Base Bid Table
Section | Bid Item |  | UofM | Est. Qty | Unit Price (USD) | Extension | Notes
1 | General Mobilization, Site Preparation and Project Support
| 1.1 | Mobilization | LS | 1 |  | 0 | Mobilization of equipment, personnel & items not otherwise specified below
| 1.2 | Project Support and Project Administration | Month | 24 |  | 0 | Office trailers, sanitary facilities, temp utilities, trash service, H&S, site inspections, construction meetings, submittals, etc.
| 1.3 | Site Preparation, Clearing, and Demolition | LS | 1 |  | 0 | Utility clearances, utility connections, clear, grub, grade, demo existing structures, E&S controls, river access, mooring area, dredge offload area, access roads, storm water management, parking area, misc debris disposal
2 | Survey and Monitoring
Survey Controls
| 2.1 | Bathymetric Surveys | LS | 1 |  | 0 | pre-con, post-organic, post-dredging
Turbidity Controls
| 2.2 | Install/Maintain Turbidity Controls around work areas | LS | 1 |  | 0
| 2.3 | Remove and Dispose of Turbidity Controls | LS | 1 |  | 0
3 | Dockwall Construction
| 3.1 | Sheetpile Dockwall Installation | LF | 1835 |  | 0
| 3.2 | CB-60 Sheetpile Support Wall | LF | 200 |  | 0
| 3.3 | Mooring Bollards | EA | 17 |  | 0
| 3.4 | Timber Rub Rail | LF | 1698 |  | 0
| 3.5 | Timber Curb | LF | 1800 |  | 0
4 | Mechanical Dredging
| 4.1 | Dredging of Organic Sediments (haul and place at Bay Port) | CY | 113380 |  | 0
| 4.2 | Dredging of Clay Soils | CY | 101530 |  | 0
5 | Earthwork
| 5.1 | Marine Stone Fill Behind Dockwall | TON | 91780 |  | 0
| 5.2 | Marine Stone Fill in Bay | TON | 55025 |  | 0 | Includes Revetment Berm Fill
| 5.3 | Marine Stone Fill in Discharge Channel | TON | 20635 |  | 0
| 5.4 | Marine Stone Fill in Boat Slip | TON | 73610 |  | 0
| 5.46 | Site Structural Fill (Clay Reused from Dredging) | CY | 75310 |  | 0
| 5.6 | 3” Breaker Run | TON | 89165 |  | 0
| 5.7 | 1 ¼” Dense Grade Crushed Stone | TON | 94260 |  | 0
| 5.8 | Revetment Berm Riprap | CY | 4425 |  | 0
| 5.9 | Remove Existing Topsoil Stockpile from Site | CY | 3350 |  | 0
| 5.1 | 1 ¼” Crushed Stone | TON | 29065 |  | 0 | Backfill for anchor wall in boat slip and north end
| 5.11 | Marine Structural Fill | TON | 20850 |  | 0 | Granular Fill above tie rods
| 5.12 | Geotextile | SY | 92750 |  | 0 | At wall backfill and across site below breaker run
| 5.13 | Cut/Fill Existing Site Grades | CY | 24650 |  | 0 | Cut/Fill Existing Grades to Bottom of Breaker Run Grades
6 | Detention Ponds and Site Drainage
| 6.1 | Excavation of Detention Ponds | CY | 32975 |  | 0
| 6.2 | Detention Ponds Clay Liner | CY | 10340 |  | 0
| 6.3 | Detention Pond Outlet Structures | EA | 2 |  | 0
| 6.4 | West Side Concrete Lined Ditch | LF | 575 |  | 0
| 6.5 | 24-inch Diameter Concrete Stormwater Pipe | LF | 1025 |  | 0
| 6.6 | Artesian Well Drain Tile | LS | 1 |  | 0
| 6.7 | Stone Drainage Swale | LF | 715 |  | 0
| 6.8 | 12-inch Diameter Concrete Stormwater Pipe | LF | 90 |  | 0
7 | Electrical Distribution and Transformers
| 7.1 | Underground Electrical, Metering Station, and Disconnect Locations (2) | LS | 1 |  | 0 | 2,460 lf of electrical feed beyond metering station by truck scale. WPS will install to metering station.
8 | Site Improvements
| 8.1 | Asphalt Pad | SY | 38720 |  | 0
| 8.2 | Truck Scale A | LS | 1 |  | 0 | Supply and Install Scale and Concrete Ramps
| 8.3 | Flint Hill Resources Dockwall Repair | LS | 1 |  | 0
9 | Demobilization and Post-Construction Activities
| 9.1 | Post-Construction Restoration | LS | 1 |  | 0
| 9.2 | Equipment and Material Demobilization | LS | 1 |  | 0
[5 empty] | Project Total: | 0
| Note: | Bidder to populate blue shaded cells only, grey shaded cells will auto fill.
Bid Schedule B - Optional Bid Items
| Bid Item |  | UofM | Est. Qty | Unit Price (USD) | Extension | Notes
Optional Bid Items
| B1 | Crane Pad | EA | 1 |  | 0 | Concrete pad and support piles
| B2 | Additional Scale | LS | 1 |  | 0
| B3 | Sanitary Sewer Installation | LF | 1240 |  | 0
| B4 | Water Line Installation | LF | 1200 |  | 0
| B5 | Security Lighting and Poles | EA | 10 |  | 0 | Assume 360 lineal feet of electrical feed per pole.
| B6 | Access Road Paving | SY | 5750 |  | 0
| B7 | Asphalt Pad Additional 4 acres | SY | 19360 |  | 0
| B8 | Import Structural Fill from Offsite Source | CY | 1 |  | 0 | Clay from BC South LF or Contractor's own source
| B9 | Vibration Monitoring | LS | 1 |  | 0 | Existing dock wall and sanitary sewer tunnel
10 | Alternatives for Value Engineering Propositions (add rows as needed)
| 10.1 |  |  |  |  | 0
| 10.2 |  |  |  |  | 0
| 10.3 |  |  |  |  | 0
| 10.4 |  |  |  |  | 0
| 10.5 |  |  |  |  | 0
| 10.6 |  |  |  |  | 0
[5 empty] | Total: | 0